## Instructions (EXTERNAL)
London Borough of Brent LFRMS Action Plan
The Action Plan supports the delivery of the London Borough of Brent LFRMS.
It is intended to be used by the Brent Lead Local Flood Authority. (FOR EXTERNAL USE)
Version: 2.0
Last Updated: February 2025
LFRMS Strategic Objectives
A | Improve our knowledge and understanding of the different flood risks in Brent
B | Improve clarity on the roles and responsibilities surrounding flooding
C | Reduce the risk of flooding to the community in Brent by delivering targeted Flood Alleviation Schemes (FASs) and encouraging the use of Sustainable Drainage Systems (SuDS)
D | Improve community awareness of flood risk and support successful communication to develop resilience to flooding in Brent
E | Maximise sustainability benefits to take a holistic approach to flood management, taking into account the impact of climate change
F | Identify funding and resources available to encourage future development within flood risk management in Brent
Table headings/sections
Actions |  | Information relating to each action and associated objective.
Funding |  | Estimated cost for action delivery and potential funding sources required.
Delivery |  | The proposed RMAs involved in the delivery of each action.
Programme |  | Proposed timescales for the action and each action's current status of progress.
Monitoring |  | Information on the monitoring procedure and regularity with any additional comments on progress of the LFRMS action.
Items
Strategic Objective |  |  | Strategic objective letter as defined in the LFRMS document.
Action ID |  |  | The individual action ID value.
Action Details |  |  | Action description.
Lead Risk Management Authority |  |  | The organisation which will lead in the delivery of the action.
Partner Authorities / Departments |  |  | The organisations which will support the delivery of the action.
Timescale from 2025 |  |  | The approximate time period for completing the action from the publication of the LFRMS, or if the action is an ongoing deliverable.
Current Status |  |  | The current status of the actions progress in being completed.
Links to Legislation / Policy |  |  | Hyperlinks to legislation that links to the delivery of this action. FWMA = Flood and Water Management Act 2010 NFCERMS = National Flood and Coastal Erosion Risk Management Strategy SWMP = Surface Water Management Plan (SWMP) Action Plan Brent Borough Plan Brent Climate Adaption and Resilience Plan Brent Climate & Ecological Emergency Strategy Brent Draft Air Quality Action Plan Brent Green Infrastruture Vision Brent Local Plan
Dropdowns
Timescale from 2025 |  |  | Current Status
Short-term = 0-2 years |  |  | Red | Action is not currently in progress
Medium-term = 2-4 years |  |  | Amber | Action is in progress
Long-term = 4-6+ years |  |  | Green | Action completed
On-going = Continual action

## LFRMS Action Plan (EXTERNAL)
London Borough of Brent LFRMS Action Plan
The Action Plan supports the delivery of the London Borough of Brent LFRMS.
It is intended to be used by the Brent Lead Local Flood Authority (LLFA). (FOR EXTERNAL USE)
Refer to the 'Instructions' Tab for a description of the contents of the Action Plan.
Version: 2.0
Last Updated: February 2025
Actions |  |  | Delivery |  | Programme |  | Links to Legislation / Policy
Strategic Objective | Action ID | Action Details | Lead Risk Management Authority | Partner Authorities / Departments | Timescale from 2025 | Current Status
A Improve our knowledge and understanding of the different flood risks in Brent | A1 | Continue to update flood webpages and mapping (i.e. West London SFRA) to ensure that the information and layers are up to date with the latest information and made easily accessible to the public. | Brent LLFA | Brent Web Team, West London Boroughs | Ongoing | Amber | FWMA
| A2 | Create and continue to maintain detailed records of instances of flooding using a suitable reporting tool, making improvements where necessary, to improve data collection on flooding within Brent. This will also support the sharing of flood reports between RMAs. | Brent LLFA | Environment Agency, Thames Water | Ongoing | Amber | NFCERMS - Measure 2.5.1
| A3 | Collaborate with other partner RMAs to improve understanding of flood risk interactions and identify areas where flood risks could combine to exacerbate risk. | Brent LLFA | Neighbouring Borough LLFAs (London Boroughs of Barnet, Camden, Ealing, Hammersmith & Fulham, Harrow, Kensington & Chelsea, and Westminster), Environment Agency, Thames Water | Short-term | Red
| A4 | Review the flood investigation criteria for when a Section 19 Investigation is required, to ensure that it is suitable and is still being applied where required. Make sure that this information is clearly visible on the website and any Section 19 Investigations are published. | Brent LLFA | Brent Emergency Planning team | Short-term | Red | FWMA - Section 19
| A5 | Continue to attend regional meetings including Drain London, LoDEG and the North West London Flood Partnership to ensure that Brent's flood risk activities coordinate with the rest of London and that Brent is aware of any future funding opportunities. | Brent LLFA | Environment Agency, Thames Water, Thames Flood Advisors, Neighbouring Borough LLFAs | Ongoing | Red
| A6 | Make sure any strategic documents and corresponding Action Plans remain current and up to date, i.e. the LFRMS, SWMP, and SFRA. | Brent LLFA | Brent Planning Team | Ongoing | Amber | FWMA
Brent Climate Adaptation and Resilience Plan
| A7 | Ensure that there is continued implementation of the Thames Flood Risk Management Plan (2021-2027) and the objectives within it, specifically those owned by Brent. Review and update the implementation status of each of Brent's measures annually. | Brent LLFA | Environment Agency, other Risk Management Authorities involved | Ongoing | Red | Flood Risk Management Plans 2021 - 2027
| A8 | Check that the current Multi-Agency Flood Plan is up to date and that officers in all council departments are familiar with it to ensure efficient responses to flooding incidents and emergency recovery following a flooding event. | Brent Emergency Planning team | Internal Council Teams | Short-term | Red
B Improve clarity on the roles and responsibilities surrounding flooding | B1 | Review and update RMA and key stakeholder contact lists. | Brent LLFA |  | Ongoing | Red
| B2 | Update and continue to maintain Brent's Asset Register to ensure that assets are identified where they have a significant impact on flood risk, so that the appropriate maintenance plans can be put in place. | Brent LLFA | Brent GIS Team, Brent Highways Team | Medium-term | Red | FWMA - Section 21
| B3 | Work together with neighbouring boroughs to identify where cross boundary flooding has or could occur, to establish and share responsibilities for collaborative flood risk management between departments. | Brent LLFA | London Boroughs of Barnet, Camden, Ealing, Hammersmith & Fulham, Harrow, Kensington & Chelsea, and Westminster, Environment Agency | Ongoing | Red | NFCERMS - Measure 2.5.1
| B4 | Start an internal flood group to facilitate the efficient use of Council resources, establish policies and share responsibilities for collaborative flood risk management between departments. | Brent LLFA | Internal Council Teams | Ongoing | Red
C Reduce the risk of flooding to the community in Brent by delivering targeted Flood Alleviation Schemes (FASs) and encouraging the use of Sustainable Drainage Systems (SuDS) | C1 | Continue developing the Woodcock Park Feasibility Study, and identify opportunities for FASs using this study. | Brent LLFA | Environment Agency, Thames Water | Ongoing | Red | NFCERMS - Measure 1.4.3
| C2 | Progress any other modelling opportunities and feasibility studies, particularly in the surface water flooding hotspots within the borough, to support ongoing development and understanding of flood risk. | Brent LLFA | Environment Agency, Thames Water | Ongoing | Red | NFCERMS - Measure 1.4.3
| C3 | Deliver targeted and appropriate FASs in response to feasibility studies and in response to flood investigations in areas which have experienced significant incidents of flooding, for example the Brondesbury Park/Kilburn areas. Liaise with the Environment Agency to secure Grant in Aid funding where appropriate. | Brent LLFA | Environment Agency, Thames Water, Thames Flood Advisors | Ongoing | Red | NFCERMS - Measure 1.4.3
Brent Climate & Ecological Emergency Strategy
| C4 | Use any Section 19 Investigations, flooding reports, and surface water mapping to continue to identify areas most at risk which could benefit from future FASs. | Brent LLFA | Environment Agency | Ongoing | Amber | NFCERMS - Measure 1.4.3
| C5 | Encourage the implementation of green infrastructure across Brent which should be located, planned, designed, and maintained to be resilient to climate change. Development should set out opportunities to create new habitats that will provide multiple benefits as part of green infrastructure. | Brent LLFA | Internal Council Teams | Ongoing | Red | Brent Borough Plan - Strategic Priority 2
Brent Local Plan - Policy BGI1
Brent Draft Air Quality Action Plan - Action L1
Brent Green Infrastructure Vision
| C6 | Investigate potential locations where nature-based solutions could be implemented within Brent. | Brent LLFA | Environment Agency, Local Community and Resident Groups | Ongoing | Red | Brent Climate & Ecological Emergency Strategy
| C7 | Work together with the Planning team in Brent to ensure that current legislation is followed and SuDS are promoted for any new developments to encourage local flood risk management. Provide training sessions to Brent Council Planning staff on sustainable drainage systems. | Brent LLFA | Brent Planning Team | Ongoing | Red | NFCERMS - Measure 2.1.4 NFCERMS - Measure 3.1.2
Brent Local Plan - Policy BSUI3 and BSUI4
Brent Climate Adaptation and Resilience Plan
Brent Green Infrastructure Vision
| C8 | Prepare an implementation plan should Schedule 3 be implemented in England, in line with guidance, to ensure that Brent is prepared for these changes. | Brent LLFA | DEFRA, Environment Agency, Brent Planning Team | Short-term | Red | FWMA - Schedule 3
D Improve community awareness of flood risk and support successful communication to develop resilience to flooding in Brent | D1 | Communicate with housing associations, community groups, charities and other organisations to improve local understanding of flood risk and the duties of the Lead Local Flood Authority. This should include advice on when flooding is an issue to highlight the importance of NFM at a catchment level and provide understanding of when flooding is acceptable, for example in open spaces and wet woodlands. | Brent LLFA | Brent Housing Team, Brent Communications Team, Community groups and charities | Short-term | Red | NFCERMS - Measure 2.1.1 NFCERMS - Measure 2.5.2
| D2 | Look into setting up Flood Action Groups, particularly within hotspot areas that are at particular risk of flooding. | Brent LLFA | Brent Housing Team, Brent Communications Team, Community groups and charities | Medium-term | Red
| D3 | Continue to update the communication plan on Brent's website to enable residents to help themselves by providing information and improving their understanding of property-level resistance and resilience measures, and how residents can access reliable flood warning systems. Undertake promotion activities to raise awareness of surface water flood risk, including posts on the website and social media. | Brent LLFA | Brent Web Team | Ongoing | Red | NFCERMS - Measure 3.1.2 NFCERMS - Measure 3.1.3
Brent Climate & Ecological Emergency Strategy - Action ACE03
Brent Climate Adaptation and Resilience Plan
Brent Green Infrastructure Vision
| D4 | Ensure that the community (including any local Flood Action Groups) is engaged in local FASs from initial development stages and throughout the development process. | Brent LLFA | Brent Communications Team | Ongoing | Red
E Maximise sustainability benefits to take a holistic approach to flood management, taking into account the impact of climate change | E1 | Review Brent's climate change targets and put in place measures where flood risk management work can align or support these. | Brent LLFA, Brent Climate Emergency Team |  | Long-term | Red | NFCERMS - Measure 2.2.2
Brent Climate Adaptation and Resilience Plan
| E2 | Review the emerging climate change projections in line with existing and updated flood risk assessments, and so review the need to update any existing guidance and strategic documents. | Brent LLFA | Brent Planning Team | Long-term | Red
| E3 | Maximise opportunities in improving biodiversity when delivering FASs by contributing to net environmental/biodiversity gain. These should be linked to Local Nature Recovery Strategies (LNRS) with the aim of establishing larger, more resilient networks of high-quality habitats across the landscape. | Brent LLFA, Brent Climate Emergency Team |  | Short-term | Red | NFCERMS - Measure 1.4.2 NFCERMS - Measure 2.2.1
Brent Borough Plan - Strategic Priority 2
Brent Local Plan - Policy BGI1
Brent Climate & Ecological Emergency Strategy
London's Local Nature Recovery Strategy
| E4 | Investigate the impacts of FASs on carbon and identify ways for reducing Brent's carbon footprint within flood risk management with the aim of being carbon neutral. This should involve the consideration of responding to climate change mitigation through natural carbon offsetting solutions. | Brent LLFA | Environment Agency, Brent Climate Emergency Team | Long-term | Red | NFCERMS - Measure 3.5.3
Brent Borough Plan - Strategic Priority 2
Brent Climate & Ecological Emergency Strategy
F Identify funding and resources available to encourage future development within flood risk management in Brent | F1 | Identify potential funding sources for the potential schemes that may be able to be delivered from the Woodcock Park feasibility study, and also for other potential flood alleviation schemes that will be developed in Brent. | Brent LLFA | Environment Agency, Thames Water, Thames Flood Advisors | Short-term | Red | NFCERMS - Measure B.1
| F2 | Keep an up to date list of ongoing and future funding opportunities to check regularly against potential schemes. This should include details on funding source, amount, timescales and requirements of the funding. | Brent LLFA | Environment Agency, Thames Water, Thames Flood Advisors | Ongoing | Red | NFCERMS - Measure B.1